## International Travel
Task List TEMPLATE - International Travel
Pre-approval
1 | Preliminary budget for approval - identify if an additional field trip fee is required from students
2 | Travel approval forms for all staff - please see O:\Staff\finance\public\Travel
3 | Once approval form the Dean or designate is received, submit forms for field trip number to finance (travelandexpenseclaims@royalroads.ca )
4 | Work with marketing in regards to website inclusion of additional fees for prospective students if required
Upon approval
1 | Notification to students of travel option for academic course. Include location, date and costs payable to RRU (field trip fee) or costs incurred by the student
2 | Orientation (can use attached power point template and deliver online or recorded)
3 | Discussion of what fees cover and additional costs for students (eg. Are they purchasing their own flights, do they need to buy their own health insurance, etc.)
4 | Adapt IFE form for students if additional fee is required
5 | Course copy "Student Travel Site" on moodle and edit or add relevant information for your trip
12 months prior to travel
1 | Confirm enough students are registered to make budget viable (Correspondence 1 template)
2 | Confirm students on trip (register in course, or invoice fee with clear instructions on confirmation process and waitlists )
3 | Enrol students in "Student Travel" moodle site for your trip
4 | Confirm with students (Correspondence 2 template)
5 | Registration in SOS system
11 months before trip
1 | Confirm trip itinerary, create schedule
2 | Book guests, accommodations or activities as needed
3 | Staff and faculty flights booked
9 – 10 months before trip
1 | Check "Student Travel" moodle site to ensure all forms are being submitted and policies being read
2 | Correspondence 3 template to update details
3 | Confirm faculty, staff and student passports meet requirements of destination country (eg. Valid for 6 months after return)
8 months before trip
1 | Monitor Government of Canada website for trip advisories
2 | Reminder to submit flight itinerary to SOS (staff and students)
3 | Reminder to visit travel clinic if necessary and obtain appropriate insurance (Correspondence 4 template)
4 | **Speak with the travel team (staff/faculty) about an appropriate back up if they are unable to travel.
5 | Ensure backups have the same pre trip processes in place - (travel clinic, insurance, and emergency process orientation, etc.)
5 months before trip
1 | Deadline for all forms to be submitted and criteria for travel met
2 | Deadline for all flights to be booked and itinerary submitted to SOS
3 | Deadline to register with Canadians Abroad (Government of Canada)
4 | Collect contact numbers of students while travelling
5 | Cell phone/Bank reminder to alert them to your international travel
6 | Purchase gifts for guests
7 | Check technology support for travel (IPAD, phone SIM cards)
8 | Staff and faculty should obtain Level 1 First Aid training
2 weeks prior to trip
1 | Compile and print itinerary books
2 | Ensure maps, confirmations, receipts, student info copied or accessible in country
3 | Review incident procedures
4 | Review arrival information with students
Post trip
1 | Evaluation
2 | Thanks yous and follow up with guests or hosts / Reviews on Trip Advisor for all hotels and translation companies
3 | Submit expense claim forms