## Task List - Non-course Related
Task List Template - Single-Day Activity or One-Day Trip
Pre-approval
| 1 | Preliminary budget for approval - identify if an additional field trip fee is required from students
| 2 | Travel approval forms for all staff - please see O:\Staff\finance\public\Travel
| 3 | Once approval form the Dean or designate is received, submit forms for field trip number to finance (travelandexpenseclaims@royalroads.ca )
Early Event Planning
| 1 | Notification to students of travel opportunity - Include location, date and costs incurred by the student if applicable
| 2 | Set date for Trip Orientation (can use attached power point template and deliver online or recorded)
| 3 | Course copy "Student Travel Site" on moodle and edit or add relevant information for your trip *Only if travel outside of the Greater Victoria region and travel is greater than 1 day
| 4 | Coordinate staged student communications (using sample correspondence templates)
| 5 | Select backup for staff/faculty and ensure they are oriented on emergency process and have proper documentation in place.
Event Preparation
| 1 | Confirm students on trip
| 2 | Enrol students in "Student Travel" moodle site for your trip *Only if travel outside of the Greater Victoria region and travel is greater than 1 day
| 3 | Facilitate staged student communications
| 4 | Registration in SOS system *Only if travel outside of the Greater Victoria region and travel is greater than 1 day
| 5 | Confirm deadline for the submission of all forms
4-8 weeks prior
| 1 | Confirm trip itinerary, create schedule
| 2 | Book guests, accommodations or activities as needed
| 3 | Staff and faculty flights booked if applicable
| 4 | Ensure documentation required for destination (eg. Passport or Driver Licence) are identified
2-4 weeks prior
| 1 | Deadline for all forms to be submitted and criteria for travel met
| 2 | Deadline for all flights to be booked and itinerary submitted to SOS
| 3 | Check "Student Travel" moodle site to ensure all forms are being submitted and policies being read if applicable
| 4 | Collect contact numbers of students while travelling
| 5 | Purchase gifts for guests
| 6 | Check technology support for travel (IPAD, phone SIM cards)
| 7 | Compile and print itinerary
| 8 | Ensure maps, confirmations, receipts, student info copied or accessible in country
| 9 | Review incident procedures
| 10 | Review arrival information with students
Post Trip
| 1 | Evaluation
| 2 | Thanks yous and follow up with guests or hosts / Reviews on Trip Advisor for all hotels and translation companies
| 3 | Submit expense claim forms