## Domestic Travel
Task List Template - Mutti-day Off-Campus Trip
Y/N | Pre-approval
| 1 | Preliminary budget for approval - identify if an additional field trip fee is required from students
| 2 | Travel approval forms for all staff - please see O:\Staff\finance\public\Travel
| 3 | Once approval form the Dean or designate is received, submit forms for field trip number to finance (travelandexpenseclaims@royalroads.ca )
| 4 | Work with marketing in regards to website inclusion of additional fees for prospective students if required
Upon approval
| 1 | Notification to students of travel option for academic course. Include location, date and costs payable to RRU (field trip fee) or costs incurred by the student if applicable
| 2 | Orientation (can use attached power point template and deliver online or recorded)
| 3 | Discussion of what fees cover and additional costs for students (eg. Are they purchasing their own flights, are they responsible for a taxi or bus to the location)
| 4 | Adapt IFE form for students if additional fee is required
| 5 | Course copy "Student Travel Site" on moodle and edit or add relevant information for your trip *Only if travel outside of the Greater Victoria region and travel is greater than 1 day
12 months prior to travel
| 1 | Confirm enough students are registered to make budget viable (Correspondence 1 template)
| 2 | Confirm students on trip (register in course, or invoice fee with clear instructions on confirmation process and waitlists )
| 3 | Enrol students in "Student Travel" moodle site for your trip *Only if travel outside of the Greater Victoria region and travel is greater than 1 day
| 4 | Confirm with students (Correspondence 2 template)
| 5 | Registration in SOS system *Only if travel outside of the Greater Victoria region and travel is greater than 1 day
11 months before trip
| 1 | Confirm trip itinerary, create schedule
| 2 | Book guests, accommodations or activities as needed
| 3 | Staff and faculty flights booked if applicable
9 – 10 months before trip
| 1 | Check "Student Travel" moodle site to ensure all forms are being submitted and policies being read if applicable
| 2 | Correspondence 3 template to update details
| 3 | Ensure documentation required for destination (eg. Passport or Driver Licence) are identified
| 4 | Identify backups for faculty/staff and ensure their documentation is in order, and they are aware of emergency process.
8 months before trip
| 1 | Monitor Government of Canada website for trip advisories
| 2 | Reminder to submit flight itinerary to SOS (staff and students)
| 3 | Reminder to visit travel clinic if necessary and obtain appropriate insurance (Correspondence 4 template)
5 months before trip
| 1 | Deadline for all forms to be submitted and criteria for travel met
| 2 | Deadline for all flights to be booked and itinerary submitted to SOS
| 3 | Deadline to register with Canadians Abroad (Government of Canada)
| 4 | Collect contact numbers of students while travelling
| 5 | Cell phone/Bank reminder to alert them to your international travel
| 6 | Purchase gifts for guests
| 7 | Check technology support for travel (IPAD, phone SIM cards)
| 8 | Staff and faculty should obtain Level 1 First Aid training
2 weeks prior
| 1 | Compile and print itinerary books
| 2 | Ensure maps, confirmations, receipts, student info copied or accessible in country
| 3 | Review incident procedures
| 4 | Review arrival information with students
Post trip
Evaluation
Thanks yous and follow up with guests or hosts / Reviews on Trip Advisor for all hotels and translation companies
Submit expense claim forms